## 16dec
| ACD_REF | SSP_ID | DEV_PLAN_END_DT | REQUIREMENT | RESOURCE_NAME | PLSQL_RESOURCE | JAVA_RESOURCE | SUPPORT_STS | REMARKS | INTERNAL_REMARKS | QC_REMARKS
1 | P11_GGI_CC_009 | GGINEW-1820489 | 2020-12-07 | Provision will be available on Quotation/Endorsement wise with the Payment term as per GGI Policy/Modification required. If the UWR checks the Modification Required system will change the status to Credit Control Approval Required. An email through My activity will be sent to Credit Control team. There will be an option for the Credit Control to approve and add comments for this transaction which requires modification. Once the modification is approved by Credit Control system will change the status of the Quotation to Quotation Pending status. Also email will be sent to the UWR who has asked for the Credit Control i.e. it will appear in his queue. The same process is applicable by Endorsement. In the Installment screen ppw days ppw due date will be displayed. | Devika | Mythili | Nandhini | Pending | 17dec : Check and fix | Check the entire functionality with W/F what we did for AE and ship the call. Mythili already verified. check with her | 15-DEC-2020 07:12:35 PM- Credit control user is not able to click on the task from My Activity and approve the quote. Clicking on the task user is redirected to login page
2 | P11_GGI_016 | GGINEW-1820287 | 2020-12-08 | Hypothecation will be used at Risk Level only. Additional field to be enabled to capture the Amount borrowed from the Bank. This should not exceed 100% but can be lesser than 100%.Details of the Hypothecation will be captured by passing Inclusion/Addition of Hypothecation endorsement. Endorsement Code ED024-(Inclusion or Deletion of Financial Interest) will be used for this functionality.Â | Devika | Mythili | Deepika | Pending | 17dec : Check and fix | Check and fix failed calls | 15-DEC-2020 06:12:14 PM- E/0003/00/P/101/1001/2020/000020344. Unable to approve endorsement Inclusion or Deletion of Financial Interest
3 | P11_GGI_038 | GGINEW-1820097 | 2020-12-09 | Provision to be made available to approve endorsement with Positive Premium as well as Negative Premium. Detailed Functional Specification Document will be shared by 3I to GGI.Â | Soma | Soma | NA | Pending | 17dec : Check and fix | Check with Ragav | 16-DEC-2020 04:12:16 PM- Unable to approve endorsements. No action, clicking on approve buttonP/101/1001/2020/000020377
4 | P11_GGI_MOT_026 | GGINEW-1820047 | 2020-12-09 | Provision to be made available to do Checklist of documents prior approval of the Quotation. This is applicable only at Quotation Level and should be auto populated once the policy conversion is made. | Janakiram | Janakiram | Nandhini | Pending | 17dec : Checklist issue to be fixed |  | 05-AUG-2020 04:08:22 PM- Apple to edit the check list even after the quote is approved and also in policy
5 | P11_GGI_180 | GGINEW-1820111 | 2020-12-10 | Facility to be available to Re-instate the Policy if it is cancelled due to Internal mistakes.Â | Narentran | Narentran | NA | Pending | 17dec : Check and fix | Check and ship the call | 16-DEC-2020 04:12:33 PM- Unable to approve endorsements. No action, clicking on approve button